## Slide 1
Prepared for
Penhallow & Brice Group
22 September 2026 · Strictly confidential
Search progress report
Chief Financial Officer
Search stage
Week 6 · Shortlist
Prepared by
Clara Voss and Imran Qadir
Template by Formatix.AI — formatix.ai/templates

## Slide 2
Penhallow & Brice Group · Chief Financial Officer · Confidential
Search at a glance
Where the search stands
Current stage
Week 6 · Shortlist
146
Researched
58
Approached
21
Interested
11
Interviewed
5
Shortlisted
Researched = organisations and individuals mapped against the brief; figures as at 22 September 2026.
A strong field: five candidates are shortlisted for client interviews, two of them sitting CFOs, and the timetable to first interviews on 6 October is holding.
Timeline
Done
Current stage
Next
11 Aug
Briefing & search strategy
Done
18 Aug
Market mapping
Done
1 Sep
Approach & first interviews
Done
22 Sep
Shortlist presented
Current stage
6 Oct
Client interviews
Next
27 Oct
Offer & references
Next
Figures as at the report date, from the search tracker · Template by Formatix.AI — formatix.ai/templates
‹#›

## Slide 3
Penhallow & Brice Group · Chief Financial Officer · Confidential
Candidate pipeline
Where every candidate stands
Candidate | Current employer | Stage | Status | Next step
Candidate A | Tolland Marine & Energy | Shortlist | Interested | Client interview 6 Oct
Candidate B | Greyhaven Utilities | Shortlist | Interested | Client interview 6 Oct
Candidate C | Orrin Specialty Chemicals | Shortlist | Interested | Client interview 7 Oct
Candidate D | Kestle Foods plc | Shortlist | Considering | Call on package, 25 Sep
Candidate E | Marrow Street Capital | Shortlist | Interested | Client interview 8 Oct
Candidate F | Brackwater Logistics | Interviewed | Reserve | Hold; update in two weeks
Candidate G | Selby Arden Holdings | Interviewed | Withdrew | None (counter-offer)
Candidate H | Northgate Rail Services | Approached | In discussion | First interview 29 Sep
Candidates may be anonymised until they agree to be named · Template by Formatix.AI — formatix.ai/templates
‹#›

## Slide 4
Penhallow & Brice Group · Chief Financial Officer · Confidential
Market feedback, risks and next steps
What we are hearing, and what happens next
Market feedback
Strong interest in the M&A agenda; candidates see the role as a step up in scope
Base salary is in line with the market, but the long-term incentive is below sector peers
Two candidates asked for more detail on the board's appetite for further acquisitions
The Leeds location is a positive for northern candidates and a hurdle for London ones
Risks and mitigations
Risk or issue | Mitigation
Long-term incentive below the market for sitting CFOs | Client to confirm LTIP flexibility before interviews; two candidates will not move without it
Candidate D has a six-month notice period | Discuss buy-out or an interim arrangement at offer stage
Next steps
Action | Owner | By
Confirm the client interview panel and schedule | Penhallow & Brice | 26 Sep
Send candidate briefing packs | Clara Voss | 30 Sep
Confirm LTIP flexibility for the offer | Group HR Director | 3 Oct
First-round client interviews | Client panel | 6–8 Oct
Market feedback is reported as heard and is not attributed · Template by Formatix.AI — formatix.ai/templates
‹#›